ANNEX II: TERMS OF REFERENCE

1.	BACKGROUND INFORMATION	2

1.1.	Partner country	2

1.2.	Contracting Authority	2

1.3.	Country background	2

1.4.	Current situation in the sector	2

1.5.	Related programmes and other donor activities	3

2.	OBJECTIVE, PURPOSE & EXPECTED RESULTS	3

2.1.	Overall objective	3

2.2.	Purpose	3

2.3.	Results to be achieved by the Contractor	4

3.	ASSUMPTIONS & RISKS	4

3.1.	Assumptions underlying the project	4

3.2.	Risks	5

4.	SCOPE OF THE WORK	5

4.1.	General	5

4.2.	Specific work	6

4.3.	Project management	7

5.	LOGISTICS AND TIMING	8

5.1.	Location	8

5.2.	Start date & Period of implementation of tasks	8

6.	REQUIREMENTS	8

6.1.	Staff	8

6.2.	Office accommodation	10

6.3.	Facilities to be provided by the Contractor	10

6.4.	Equipment	10

7.	REPORTS	10

7.1.	Reporting requirements	10

7.2.	Submission and approval of reports	11

8.	MONITORING AND EVALUATION	11

8.1.	Definition of indicators	11

8.2.	Special requirements	11

# BACKGROUND INFORMATION

## Partner country

Republic of Serbia, Autonomous Province of Vojvodina

## Contracting authority

Provincial Secretariat for Education, Regulations, Administration and National Minorities – National Communities, Bulevar Mihajla Pupina, 21000 Novi Sad

## Country background

The rising interest in the tourism-related facilities and offers is reflected in numerous strategies and projects concerning tourism. The project itself is in line with Priority Axis 3 - To promote culture and tourism, people to people contacts of the EU Strategy for the Danube Region by offering stronger connections between people through exploitation and upgrading of the existing tourism assets.

This project also reflects the increasing interest in tourism-related activities and amenities on a regional and cross-border level. The project finds backing in the results of the project "Integrated spa development strategy for the spas situated in the area of the main traffic route through the Hungarian-Serbian cross border region" which demonstrate that the tourism related offers in the broader cross-border region can be connected to form more comprehensive, diverse and attractive tourist package. The offer of tourism-related activities and amenities in the region of the Municipality of Kanizsa could be integrated into the tourist offer of Ásotthalom, Mórahalom and Kistelek municipalities. The study financed by HU-SRB IPA CBC (Ref.no.: HUSRB/0901/213/013/001-4.2-KANJIZA) points to development of competitive tourism within Priority IV (IV.6 Creating competitive tourist products and their integration in international tourist offer).

The Municipality of Kanjiža has a great, albeit insufficiently exploited tourist potential. In addition to the existing spa and accommodation capacities, this particular region also has a lot to offer in terms of arts and culture (setting for the renown festivals such as the Palić Film Festival and Kanjiza Fest), history (the region is home to many historic buildings which represent the joint European heritage in Subotica and Kanizsa) and nature (Special Nature Reserve „Selevenjske pustare“).

## Current situation in the sector

The current situation is indicative of an underdeveloped tourist offer in the region of Kanizsa Municipality, primarily due to the outdated tourism-related infrastructure and lack of marketing on an international level. According to the SWOT analysis performed for the Kanizsa Municipality, another issue is the lack of adequate space for the organisation of outdoor sporting events. The existing resources are significantly underused - an area of 6000 m2 owned by the Municipality is neither appropriately nor completely utilised, while the site itself offers numerous advantages (vicinity of river and the city swimming pools, good connection to the vital, main road network and municipal utilities infrastructure). Additionally, the area is used for a shorter period during the year, which could be extended and its utilisation could be enhanced as a result of the project implementation.

The negative population growth and the median population age of 41 in the Kanizsa Municipality as well as large-scale migrations, particularly young people, suggests that there is also need for more quality engagement of young people in sport and informal education activities. According to the municipal strategic document, it is necessary to raise the awareness of young people of environmental issues, which is also in the focus of respective project activities. The Secretariat was conferred the purview of the field of education for the territory of the entire Autonomous Province of Vojvodina, covering 121 secondary education institutions and more than 60.000 students. In addition to the aforementioned, the Secretariat manages affairs in all fields that are relevant for implementation of projects engaging youth as the main target group. This includes legal, financial, project management and education-related affairs. Within its structure, the Secretariat also has internal organizational units which are relevant for the project as well as the Department for the Exercise of National Minority Rights and Translation Service.

- national/local policies and strategies and/or economic data for the sector or institutional area;

- The most relevant national document in SRB is Tourism Development Strategy of Republic of Serbia where is one goal establishing Serbian tourism location marketing and using internet to promote new locations for local, national and international tourists. Project is also in accordance with Marketing Strategy of Vojvodina which also put emphasis on "e Toruism and the application of modern information and communication technologies in tourism development“.

- the origin and recent history of current organisational structures, institutions and operating systems in the sector or institutional area;

- responsibilities and mandate of institutions;

- human resource capacity and constraints;

- Secretariat have delegated competence in the field of education for the territory of the entire Autonomous Province of Vojvodina. This includes cooperation with 121 secondary education institutions counting more than 60.000 students. In addition to the aforementioned, the organization structure of the Secretariat envisages management of affairs in all fields that are relevant for implementation of projects engaging youth as the main target group. This also covers accompanying legal, financial, project management and education affairs. Within its structure, the Secretariat also has internal organizational units relevant for the project as well as the Department for Exercise of National Minority Rights and Translation Service. The Secretariat have 97 employees.

## Related programmes and other donor activities

Project MATCHDO ID: 535917-LLP-1-2012-1-RS-KA1. Lifelong Learning Programme. Budget: 106 745 EUR. Project is implemented within the Lifelong Learning programme financed by the European Commission with the following project partners: the Open University Subotica, National Employment Service from Belgrade and Provincial Secretariat for Education, Administration and National Communities.

Among various projects in the field of education project “Promotion of Multiculturalism and Tolerance in Vojvodina“ financed by AP Vojvodina budget represents major and longest activity. Project has been implemented since year 2005 and it is currently in 14th phase.

# OBJECTIVE, PURPOSE & EXPECTED RESULTS

## Overall objective

The project aims to enhance the tourism potentials of the targeted area by improving and diversifying the tourist offer along the route of Kistelek and Kanjiza (Magyarkanizsa). It includes the four main project aspects each of which consists of a number of activities contributing to meeting the main project objective – to develop the tourism in the territory of Kanjiza and Kistelek Municipality. The first aspect includes the extension of the existing spa in Kistelek Municipality which would contribute to promotion of health tourism. Its objective is to provide a center where different health-lifestyle counseling and supportive medical treatment could be presented so that the attention of tourists could be guided towards health tourism.

The second aspect of the project is infrastructural development and revitalization of the existing sport capacities and construction of multifunctional sport field in Kanjiža along with the required sanitary infrastructure thus enabling utilization of otherwise unused sport capacities by visitors.

The third project aspect is aimed at organisation of the youth summer camp in Kanjiža for secondary school students.

The fourth aspect of the project is focused on the development of the web site/mobile optimized software connecting regional tourist offers on the route between Kistelek and Kanjiza offering to potential visitors specific thematic content. This aims to raise attention to the tourism opportunities of the region.

As a result, the overall project should lead to longer stay of visitors in the region as well as boost the existing tourist offer in the region through further development of the existing capacities. Additionally, the project is in line with the Priority Area 3 of the EU Strategy for the Danube Region – To promote culture and tourism, people to people contacts offering stronger connections between people and youth in the target area as well as further employing and interconnecting the existing tourist assets.

## Purpose

The purposes of this contract are as follows:

- organization of 2 summer camps

- organization of additional activities during camps – 2 orienteering competition

- organization of competitions in accordance with supplied games concept and rules

- organization of workshops in 4 secondary schools

## Results to be achieved by the contractor

- result 1 - organization of camp

- - two 4-days camps organised in succession, with 88 participants per camp

- result 2 - organization of orienteering competition

- - two competitions organised, 1 per camp

- result 3 – organization of competitive games according to supplied games concept, rules, scenery and props

- - 2 competitions organised, 1 per camp, minimum 10 competitive games per competition, 4 day duration

- result 4 – organization of workshops

- - minimum 2 workshops per school organized in 4 secondary schools in Vojvodina.

# ASSUMPTIONS & RISKS

## Assumptions underlying the project

Sufficient number of schools that submitted camp participation application

Attendance of required number of participants from each school

## Risks

- cancelation of participants that applied to camp due to unforeseen and objective circumstances

- legal aspects - parental consent issue that is needed for minors participation in events

- Force majeure – weather conditions and/or natural disasters, meteorological events, floods etc.

# SCOPE OF THE WORK

## General

### Description of the assignment

Contractor is required to implement the service of organization of two 4-days camps in Kanjiža for participants from AP Vojvodine. During each camp contractor will organize competitive games of skill and agility for participants, orienteering competition in Kanjiža and additional leisure activities.

Obligation of contractor in each camp are as follows:

- Organization of opening and closing ceremonies of the camp (stage or pavilion tent of minimal dimension 3x2 meters)

- Orienteering competition organization (coordination, preparing plans, maps and routes for event, photographing of location, social media publishing and administrating)

- Program presenter fees (two presenters, ceremonies in Serbian and Hungarian language)

- Miscellaneous equipment (balls, jump-ropes) needed for ceremonies and leisure activities

- Camp accommodation for participants (maximum of 1500 meters from City Beach in Kanjiža-Štrand, entrance from Potiski venac/Tiska street)

- Provision of tents for participants (88 participants in each camp, 8 adults, 80 secondary school students, tent capacity needed is between 2 and 14 persons)

- Sound system rental, lightning and video-wall (or equivalent) rental for camp events and ceremonies

- Additional audio and video equipment rental for competitions (if needed)

- Supporting goods provision (chairs – 30 pcs, 8 tables minimum dimensions 120x70 cm , stands)

- Promotional flags of event – beach flag (min 200 cm height)

- jersey – t shirts for participants, 200 pcs. minimum, minimum 8 different colours

- Stage installation for ceremonies

- Transportation of participants (local and regional) – transportation of participants from school location cities to Kanjiža and back (retour)

- Administrative and insurance fees for participants (if applicable)

- Security and medical care expenses (security personnel – minimum 1 person during the duration of event)

- Teachers (schools representative team leaders) allowance (16 persons per diems)

- Supporting workers and technical staff fees (competition organization team and scenery installation workers)

- Mandatory medical check of participants (each participant needs to be checked for school sport competence)

- Meals for participants and guests (breakfast, lunch, dinner, snack, beverages)

- Accommodation for guests (hotel or pansion accommodation for 6 persons, 8 days, bed and breakfast, 2 double and 2 single rooms)

All promotional material design must be in line with the Guidelines for Implementation of Information and Publicity Measures for Projects and preapproved by contracting authority.

Contractor is required to conduct coordination of workshops in 4 secondary schools in Vojvodina on the subject of regional touristic offer (Kanjiža-Kistelek route) and preparation of mobile optimised website content, that will introduce users with relevant offers between Kistelek and Kanjiza settlements. Outcomes of the workshops will deliver definition of what sites (location), activities, festivals and events and other leisure activities can be of interest for young travelers and visitors.

Obligation of contractor:

- establishing contact with 4 secondary schools in AP Vojvodina and coordination of workshop implementation;

- provision of aggregated data based on document template that will provide website content

- required elements of document template:

- Name of event/site/touristic offer

- Venue/location

- Time range/date of event (if applicable)

- Type of touristic offer (history, health tourism, cultural heritage, nature etc.)

- Keywords

- Link to website

- Description (100-1000 characters)

- Photo (if applicable)

- Website link (if applicable)

### Geographical area to be covered

Kanjiža, AP Vojvodina, Republic of Serbia

### Target groups

Target group is secondary school students from Autonomous Province of Vojvodina age 14-19. Participants will be delegated from 16 schools. Each school will delegate 10 students and 1 professor. Each camp will have 88 participants. Total of 160 students and 16 professors.

## Specific work

- Transportation of the camp participants

- Number of applied schools: 16

- Applied schools:

- GIMNAZIJA "NIKOLA TESLA", APATIN

- POLJOPRIVREDNA ŠKOLA, BAČKA TOPOLA

- SREDNJA TEHNIČKA ŠKOLA "ŠINKOVIĆ JOŽEF", BAČKA TOPOLA

- EKONOMSKO TRGOVINSKA ŠKOLA,BEČEJ

- SREDNJA STRUČNA ŠKOLA "4. JULI", VRBAS

- SREDNJA ŠKOLA "DR ĐORĐE NATOŠEVIĆ", INĐIJA

- SREDNJA STRUČNA ŠKOLA "BORISLAV MIHAJLOVIĆ MIHIZ", IRIG

- POLJOPRIVREDNO-TEHNIČKI SREDNJOŠKOLSKI CENTAR "BESEDEŠ JOŽEF", KANJIŽA

- GIMNAZIJA "MIHAJLO PUPIN", KOVAČICA

- GIMNAZIJA I EKONOMSKA ŠKOLA "BRANKO RADIČEVIĆ", KOVIN

- BALETSKA ŠKOLA "DIMITRIJE PARLIĆ", PANČEVO

- SREDNJA MEDICINSKA ŠKOLA, SENTA

- SREDNJA ŠKOLA "SVETI SAVA", SOMBOR

- SREDNJA TEHNIČKA ŠKOLA "MILEVA MARIĆ", TITEL

- OSNOVNA ŠKOLA I GIMNAZIJA "PETRO KUZMJAK", RUSKI KRSTUR

- EKONOMSKA SREDNJA ŠKOLA "BOSA MILIĆEVIĆ", SUBOTICA

- Note: Each of 2 camps will be attended by students from 8 out of 16 schools. The list of schools will be divided between two camps and the exact schedule will be determined by the Contracting Authority before the beginning of each camp.

- Specific Activity 1 – CAMP I

- Organization of a camp 1

- Location: Kanjiža

- Date: 15-18 August 2019

- Number of participants: 88  - (80 students and 8 professors) – 10 students and 1 professor from 8 of 16 schools from the list of applied schools.

- Participants: students, professors

- Duration: 4 days – start first day at 12:00 h  - end on fourth day at 16:00h ( 3 nights)

- Accommodation: 88 persons

- Water and beverages for 88 persons x 4 – minimum 2,5 litres per person per day

- Provisions of camp premises in Kanjiža for the duration of camp

- Transportation expenses coverage for 88 persons in total, covering the following route form school cities to Kanjiža and back

- Accommodation expenses for guests

- Taxes and insurance costs for camp participants for 4 days – 88 persons (if applicable)

- Organization of orienteering competition 1

- Competition for camp participants with emphasis on Kanjiža nature, cultural and touristic sites

- Preparation of competition plans and routes

- Social media publishing of photographs of event

- Organization of competition 1

- Organization of competition activities in accordance with supplied games concept -  use of open swimming pool on Kanjiža city beach (Štrand) for (1 day) and outdoor sport fields (4 day) for participants

- Minimum 10 competitive games organized

- Provision of required personnel needed for scenery setup and maintenance

- Provision of required scenery expert and games supervisor

- Provision of required referees for games – minimum 4 persons

- Specific Activity 2 – CAMP II

- Organization of a camp 2

- Location: Kanjiža

- Date: 19-22 August 2019

- Number of participants: 88  - (80 students and 8 professors) – 10 students and 1 professor from 8 of 16 schools from the list of applied schools.

- Participants: students, professors

- Duration: 4 days – start first day at 12:00 h  - end on fourth day at 16:00h ( 3 nights)

- Accommodation: 88 persons

- Water and beverages for 88 persons x 4 – minimum 2,5 litres per person per day

- Provisions of camp premises in Kanjiža for the duration of camp

- Transportation expenses coverage for 88 persons in total, covering the following route form school cities to Kanjiža and back

- Accommodation expenses for guests

- Taxes and insurance costs for camp participants for 4 days – 88 persons (if applicable)

- Organization of orienteering competition 2

- Competition for camp participants with emphasis on Kanjiža nature, cultural and touristic sites

- Preparation of competition plans and routes

- Social media publishing of photographs of event

- Organization of competition 2

- Organization of competition activities in accordance with supplied games concept -  use of open swimming pool on Kanjiža city beach (Štrand) for (1 day) and outdoor sport fields (4 day) for participants

- Minimum 10 competitive games organized

- Provision of required personnel needed for scenery setup and maintenance

- Provision of required scenery expert and games supervisor

- Provision of required referees for games – minimum 4 persons

Specific Activity 3 – WORKSHOPS COORDINATION

- Location: AP Vojvodina

- Date: 30 July - 22 August 2019

- Number of participants: minimum 8 students and 1 professor from each school, total of minimum 32 students and 4 professors

- Participants: students, professors

## Project management

### Responsible body

The Contractor is responsible for all activities regarding this contract

### Management structure

The responsible person for implementation of the tasks related to this contract, in the Contracting Authority, is Project manager.

### Facilities to be provided by the contracting authority and/or other parties

- games concept required for competition organization (further information on following http://www.puma.vojvodina.gov.rs/dokumenti/projekat/oasis/Prikaz_igara_OASIS.mp4

- scenery and props required for competition organization,

- document template for workshop implementation.

# LOGISTICS AND TIMING

## Location

Municipality of Kanjiža, AP Vojvodina, Republic of Serbia

## Start date & period of implementation of tasks

The intended start date is 26 July 2019 and the period of implementation of the contract will be 1 months from this date. Please see Articles 19.1 and 19.2 of the special conditions for the actual start date and period of implementation.

# REQUIREMENTS

## Staff

Event coordinator - a university degree in tourism/sports/sport management or a relevant, directly related discipline, or equivalent relevant professional experience, experience in coordinating similar activities of competitive events, sports events or cultural and leisure events for minimum of 3 years.

Note that civil servants and other staff of the public administration of the partner country, or of international/regional organisations based in the country, shall only be approved to work as experts if well justified. The justification should be submitted with the tender and shall include information on the added value the expert will bring as well as proof that the expert is seconded or on personal leave.

### Key experts

Not required

### Other experts, support staff & backstopping

N/A

## Office accommodation

N/A

## Facilities to be provided by the contractor

N/A

## Equipment

No equipment is to be purchased on behalf of the contracting authority / partner country as part of this service contract or transferred to the contracting authority / partner country at the end of this contract. Any equipment related to this contract which is to be acquired by the partner country must be purchased by means of a separate supply tender procedure.

# REPORTS

## Reporting requirements

The contractor will submit the following reports in English language in one original and 2 copies:

- Draft final report of maximum 5 pages (main text, excluding annexes) in the format provided by contracting authority. This report shall be submitted no later than one month before the end of the period of implementation of tasks.

- Final report with the same specifications as the draft final report, incorporating any comments received from the parties on the draft report. The deadline for sending the final report is 7 days after receipt of comments on the draft final report. The report shall contain a sufficiently detailed description of the different options to support an informed decision on accepted of report. The detailed analyses underpinning the recommendations will be presented in annexes to the main report. The final report must be provided along with the corresponding invoice.

## Submission and approval of reports

The report referred to above must be submitted to the project manager identified in the contract. The project manager is responsible for approving the reports. The approval of the final report by Project manager will be basis for payments.

# MONITORING AND EVALUATION

## Definition of indicators

Indicator 1 - attendance lists, team lists, photographs (from 2 camps)

Indicator 2 – orienteering competition plan, attendance list, results list (from 2 orienteering competitions)

Indicator 3 – score tables from competitions, results, final scores from competitions, names of winning team members (from 2 competitions)

Indicator 4 – workshop participants list, filled in documents with website content

## Special requirements

N/A